## Sheet1
Sprint | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10
| User Story | Task name | Feature type | Start Date | Finish Date | Duration | Story Points | Status | Release Date | Goal / Objective
1 | To create a login page | login page creation | UI | 2022-03-28 | 2022-03-30 | 3 days | 3 days | completed |  | To create a login page
2 | To create a register page | Register page creation | UI | 2022-03-31 | 2022-03-04 | 5 days | 5 days | completed |  | To create a register page
3 | To create a forgot password page | Forgot password page creation | UI | 2022-04-05 | 2022-04-06 | 2 days | 2 days | completed |  | To create a forgot password page
4 | To create the main page | main page creation | UI | 2022-04-07 | 2022-04-11 | 3 days | 3 days | completed |  | To create the main page
5 | To create the profile management page | profile management page creation | UI | 2022-04-14 | 2022-04-15 | 2 days | 2 days | completed |  | To create the profile management page
6 | To create a categories page | Categories page creation | UI | 2022-04-16 | 2022-04-24 | 8 days | 8 days | completed |  | To create a categories page
7 | adding profile photo in profile management page | adding profile photo in profile management page | UI | 2022-04-25 | 2022-04-26 | 2 days | 2 days | completed |  | adding profile photo in profile management page
8 | creating an expense page | expense page creation | UI | 2022-04-27 | 2022-04-28 | 2 days | 2 days | completed |  | creating an expense page
9 | creating a database | database creation | UI | 2022-04-29 | 2022-05-03 | 3 days | 3 days | completed |  | creating a database
10 | Developing a show analysis page | show analysis page creation | UI | 2022-05-05 | 2022-05-07 | 3 days | 3 days | completed |  | Developing a show analysis page
11 | Created an alert message box | alert message box creation | UI | 2022-05-10 | 2022-05-11 | 1 day | 1 day | completed |  | Created an alert message box
12 | linking the pages | linking the pages | UI | 2022-05-12 | 2022-05-13 | 1 day | 1 day | completed |  | linking the pages