## Sheet1
Unique ID | User Stories | Particulars (Today's work- Date to be mentioned) | Assignee | Reporter (Scrum Master) | Present / Absent | Status | Resolution | Created | Due | Fix Version/s | Product Backlog
1 | to create a login page | 28-03-2022- to create a login page | shravya | sravya | present | In progress | NA | 2022-03-28 | 2022-03-30 | 1 | creating a login page
2 | to create a login page | 29-03-2022- to create a login page | shravya | sravya | present | In progress | NA | 2022-03-29 | 2022-03-30 | 1 | creating a login page
3 | to create a login page | 30-03-2022- to create a login page | shravya | sravya | present | completed | NA | 2022-03-30 | 2022-03-30 | 1 | creating a login page
4 | to create a register page | 31-03-2022- to create a register page | shravya | sravya | present | in progress | NA | 2022-03-31 | 2022-04-04 | 1 | creating a register page
5 | to create a register page | 1-04-2022- to create a register page | shravya | sravya | present | in progress | NA | 2022-04-01 | 2022-04-04 | 1 | creating a register page
6 | to create a register page | 4-04-2022- to create a register page | shravya | sravya | present | completed | NA | 2022-04-04 | 2022-04-04 | 1 | creating a register page
7 | to create a forgot password page | 5-04-2022- to create a forgot password page | shravya | sravya | present | in progress | NA | 2022-04-05 | 2022-04-06 | 1 | creating a forgot password page
8 | to create a forgot password page | 6-04-2022- to create a forgot password page | shravya | sravya | present | completed | NA | 2022-04-06 | 2022-04-06 | 1 | creating a forgot password page
9 | to create a main page | 7-04-2022- to create a main page. Issue- establishing connection between the pages | preethi | sravya | present | in progress | unresolved | 2022-04-07 | 2022-04-11 | 1 | creating a main page
10 | to create a main page | 8-04-2022- to create a main page. Issue- establishing connection between the pages | preethi | sravya | present | in progress | resolved | 2022-04-08 | 2022-04-11 | 1.1 | creating a main page
11 | to create a main page | 11-04-2022- to create a main page | preethi | sravya | present | in progress | NA | 2022-04-11 | 2022-04-11 | 1.1 | creating a main page
12 | to create a profile management page | 14-04-2022-to create a profile management page | shravya | sravya | present | in progress | NA | 2022-04-14 | 2022-04-15 | 1.1 | creating a profile management page
13 | to create a profile management page | 15-04-2022-to create a profile management page | shravya | sravya | present | completed | NA | 2022-04-15 | 2022-04-15 | 1.1 | creating a profile management page
14 | to create a categories page | 16-04-2022-to create a categories page | kavya | sravya | present | in progress | NA | 2022-04-16 | 2022-04-24 | 1.1 | creating a categories page
15 | to create a categories page | 17-04-2022-to create a categories page | kavya | sravya | present | in progress | NA | 2022-04-17 | 2022-04-24 | 1.1 | creating a categories page
16 | to create a categories page | 18-04-2022-to create a categories page. Issue-displaying users input in an other frame | kavya | sravya | present | in progress | unresolved | 2022-04-18 | 2022-04-24 | 1.1 | creating a categories page
17 | to create a categories page | 19-04-2022-to create a categories page. Issue-displaying users input in an other frame | kavya | sravya | present | in progress | resolved | 2022-04-19 | 2022-04-24 | 1.2 | creating a categories page
18 | to create a categories page | 20-04-2022-to create a categories page. Issue-edit option doesnot overwrite | kavya | sravya | present | in progress | unresolved | 2022-04-20 | 2022-04-24 | 1.2 | creating a categories page
19 | to create a categories page | 23-04-2022-to create a categories page | kavya | sravya | present | in progress | unresolved | 2022-04-23 | 2022-04-24 | 1.2 | creating a categories page
20 | to create a categories page | 24-04-2022-to create a categories page | kavya | sravya | present | completed | resolved | 2022-04-24 | 2022-04-24 | 1.3 | creating a categories page
21 | adding profile photo in profile management page | 25-04-2022-adding profile photo in profile management page | shravya | sravya | present | in progress | NA | 2022-04-25 | 2022-04-26 | 1.3 | adding profile photo in profile management page
22 | adding profile photo in profile management page | 26-04-2022-adding profile photo in profile management page | shravya | sravya | present | completed | NA | 2022-04-26 | 2022-04-26 | 1.3 | adding profile photo in profile management page
23 | creating an expense page | 27-04-2022-creating an expense page | preethi | sravya | present | in progress | NA | 2022-04-27 | 2022-04-28 | 1.3 | creating an expense page
24 | creating an expense page | 28-04-2022-creating an expense page | preethi | sravya | present | completed | NA | 2022-04-28 | 2022-04-28 | 1.3 | creating an expense page
25 | creating a database | 29-04-2022-creating a database | shravya&preethi | sravya | present | in progress | NA | 2022-04-29 | 2022-05-03 | 1.3 | creating a database
26 | creating a database | 30-04-2022-creating a database | shravya&preethi | sravya | present | in progress | NA | 2022-04-30 | 2022-05-03 | 1.3 | creating a database
27 | creating a database | 3-05-2022-creating a database | shravya&preethi | sravya | present | completed | NA | 2022-05-02 | 2022-05-03 | 1.3 | creating a database
28 | Developing a show analysis page | 4-05-2022-Developing a show analysis page | shravya&kavya | sravya | present | in progress | NA | 2022-05-05 | 2022-05-07 | 1.3 | Developing a show analysis page
29 | Developing a show analysis page | 5-05-2022-Developing a show analysis page | shravya&kavya | sravya | present | in progress | NA | 2022-05-06 | 2022-05-07 | 1.3 | Developing a show analysis page
30 | Developing a show analysis page | 6-05-2022-Developing a show analysis page | shravya&kavya | sravya | present | completed | NA | 2022-05-07 | 2022-05-07 | 1.3 | Developing a show analysis page
31 | Created an alert message box | 09-05-2022-Created an alert message box | preethi | sravya | present | completed | NA | 2022-05-10 | 2022-05-11 | 1.3 | Created an alert message box
32 | linking the pages | 10-05-2022-linking the pages | shravya&preethi | sravya | present | completed | NA | 2022-05-12 | 2022-05-13 | 1.3 | linking the pages