## Sheet1
Initial Product Backlog
Ref | Description | Type | Group | Relative Value | Initial Estimate | Adjust Factor | Estimate | Release | Sprint | Status
1 | Creating a login page for expense tracker webpage with fields of username and password including register and forgot password options | feature | front-end development | 10 | 3 | 1 | 4 | 1 | 1 | done
2 | Developing a user register page which includes first name, last name, contact, email, security question and security answer. | feature | front-end development and back-end development | 10 | 5 | 0 | 5 | 1 | 1 | done
3 | Developing a forgot password page which includes security question and reset password options | feature | front-end development and back-end development | 10 | 2 | 0 | 2 | 1 | 1 | done
4 | Developing the main page for the application. It consists of a side bar which consists of various sub pages which includes profile management, settings management, show analysis. | feature | front-end development | 10 | 3 | 0 | 3 | 1 | 1 | done
5 | Developing a profile management page which includes user information such as first name, last name, email, phone number, edit button. On clicking edit button details can be modified | feature | front-end development and back-end development | 10 | 2 | 1 | 3 | 1 | 1 | done
6 | On clicking settings management button we get an option to see the different categories and we can see the max limit to spend in each category. In other option we can add new category and the max limit we can spend. There is an edit option which allows us to change the max limit we can spend | feature | front-end development | 10 | 8 | 1 | 9 | 1 | 1 | done
7 | In the profile management page we added the option to insert the profile picture and also update it if intrested. The profile picture is saved along with the personal information | feature | front-end development and back-end development | 10 | 2 | 1 | 3 | 1 | 2 | done
8 | Developing an expenses page which allows you to add the expenses along with the date of transaction, category under which it falls and the mode of payment. It also displays the list of expenses | feature | front-end development and back-end development | 10 | 2 | 0 | 2 | 1 | 2 | done
9 | Creating a database to store the values entered through the register page, forgot password page, profile management page, categories page, add expense page and linking the tables with their respective pages | feature | back-end development | 10 | 3 | 0 | 3 | 1 | 2 | done
10 | Developing a show analysis page which displays the different transactions and analyses the data. It also displays the amount that can be transacted based on the maximum limit | feature | front-end development and back-end development | 10 | 3 | 1 | 4 | 1 | 2 | done
11 | Created an alert message box that alerts user if the maximum limit for the expenses is reached and the amount left to spend under each category | feature | front-end development and back-end development | 10 | 1 | 0 | 1 | 1 | 2 | done
12 | Linking the main page containing the side bar with the profile management page, settings page, add expenses page and the show analysis page. Also linking the login and register page with the main page | feature | front-end development | 10 | 1 | 0 | 1 | 1 | 2 | done